LAKE TAHOE LICENSE PLATE MARKETING & OUTREACH

The Tahoe Fund is proposing a 12-month marketing and outreach effort to help promote license plate sales with two large campaigns occurring in the winter and summer months.

The Plate for Powder Program is the first of the two campaigns that will run from December 12th through April 15th. Lake Tahoe-area ski resorts in California and Nevada are offering two free lift or Nordic tickets for every purchase of a California or Nevada Lake Tahoe license plate ordered through the tahoefund.org or tahoeplates.org sites.

The schedule and budget for the overall marketing and outreach effort is outlined below.

WORKPLAN SCHEDULE

Task	Task Completed

Contract signed	October 2011

Pre-campaign meetings and strategy completed	October 2011

Outreach to ski and cross-country resorts completed	November 2011

Plate for Powder Program collateral/advertising completed	November 2011

Email blast template completed; email blast #1 distributed	November 2011

Website updates and social media infrastructure completed	November 2011

Collateral printed (general rack card, DMV display, event booth materials)	January 2012

Calendar of events completed (booth participation)	January 2012

Email blast #2 distributed	February 2012

DMV displays and rack cards distributed	February 2012

Plate for Powder Program completed	May 2012

Summer campaign collateral/advertising completed	May 2012

Website and social media landing pages updated	May 2012

Email blast #3 distributed	May 2012

Replenishment/additional distribution of rack cards/displays completed	June 2012

Email blast #4 distributed	August 2012

News release distribution	On-going, monthly

Public-private partnership outreach	On-going, monthly

Outreach for Web linking campaigns and in-linking opportunities	On-going, monthly

Social Media posting	On-going, monthly

Measurement and reporting	On-going, monthly

BUDGET/COST PROPOSAL

|  | Personnel | Hrs | Rate | Amount $ | In-Kind |
| --- | --- | --- | --- | --- | --- |
| Public Relations |  |  |  | $9,320.00 | $3,280.00 |
| Writing of 12 news releases | SDBX | 55 | $100/hr | $5,500.00 |  |
| Proofing & Distribution | SDBX | 12 | $85/hr | $1,020.00 | $180.00 |
| Media list maintenance | SDBX | 10 | $30/hr | $300.00 | $700.00 |
| Tracking & Reporting | SDBX | 15 | $100/hr | $1,500.00 |  |
| Writing PSAs (2–3) | SDBX | 10 | $100/hr | $1,000.00 |  |
| Cision Media database | SDBX |  |  |  | $2,400.00 |
| Advertising |  |  |  | $45,530.00 | $14,270.00 |
| Campaign Strategy & Development | All | 40 | $100/hr | $4,000.00 |  |
| Print & online ad templates | SDBX | 18 | $85/hr | $1,530.00 | $270.00 |
| Media plan buy/execution; tracking and reporting | CC |  | cost | $40,000.00 | $14,000.00 |
| Print Collateral |  |  |  | $14,805.00 | $795.00 |
| Rack card design, general | SDBX | 8 | $85/hr | $680.00 | $120.00 |
| Rack card/display design, plate for powder program | SDBX | 7 | $85/hr | $595.00 | $105.00 |
| Rack card copywriting | SDBX | 8 | $100/hr | $800.00 |  |
| Rack card printing | Printer |  | cost | $4,500.00 |  |
| DMV & car dealership display | SDBX | 20 | $85/hr | $1,700.00 | $300.00 |
| DMV & car dealership display copywriting | SDBX | 4 | $85/hr | $340.00 | $60.00 |
| DMV & car dealership printing | Printer |  | cost | $5,000.00 |  |
| Local/regional events research | SDBX | 4 | $85/hr | $340.00 | $60.00 |
| Booth display materials | SDBX | 10 | $85/hr | $850.00 | $150.00 |
| Online Marketing |  |  |  | $29,420.00 | $3,480.00 |
| Web site updates (2 campaigns) | SDBX | 100 | $95/hr | $9,500.00 | $500.00 |
| Template banner ad/badge (2 campaigns) | SDBX | 8 | $85/hr | $680.00 | $120.00 |
| Email template (design & build) | SDBX | 14 | $85/hr | $1,190.00 | $210.00 |
| Email template updates (x4) | SDBX | 20 | $85/hr | $1,700.00 | $300.00 |
| Email distribution (x4) | Vendor |  | cost | $500.00 |  |
| Email blast copywriting (x4) | SDBX | 12 | $100/hr | $1,200.00 |  |
| SM strategy & implementation | SDBX | 100 | $85/hr | $8,500.00 | $1,500.00 |
| FB page development: 6 tabs | SDBX | 20 | $95/hr | $1,900.00 | $100.00 |
| SEO / Inlinking opps | SDBX | 50 | $85/hr | $4,250.00 | $750.00 |
| Partnership Building |  |  |  | $14,450.00 | $36,000.00 |
| Plate for Powder program maintenance | TF | 60 | $85hr | $5,100.00 | $36,000.00 |
| Additional campaign maintenance | TF | 60 | $85/hr | $5,100.00 |  |
| Public transportation, gov't and enviro org outreach | TF | 8 | $85hr | $680.00 |  |
| Chambers outreach | TF | 8 | $85hr | $680.00 |  |
| Community Foundation outreach | TF | 8 | $85hr | $680.00 |  |
| Vacation Rental outreach | TF | 8 | $85hr | $680.00 |  |
| Lodging, local biz outreach | TF | 10 | $85hr | $850.00 |  |
| PUD outreach | TF | 8 | $85hr | $680.00 |  |
| Measurement, Reporting & Project Management |  |  |  | $6,375.00 |  |
| Project management & reporting | TF | 75 | $85/hr | $6,375.00 |  |
|  |  |  |  | Total Amount | Total In-Kind |
|  |  |  |  | $119,900.00 | $57,825.00 |